**Phase 1: Development**

* Task 1: Set up the development environment (1 day)
* Task 2: Develop the user management system (3 days)
* Task 3: Develop the course search by code feature (2 days)
* Task 4: Develop the comment section feature (2 days)
* Task 5: Develop the general forum feature (3 days)
* Task 6: Develop the quiz and practice questions feature (4 days)
* Task 7: Develop the material management feature (4 days)

**Phase 2: Testing and Validation**

* Task 1: Test the user management system (2 days)
* Task 2: Test the course search by code feature (1 day)
* Task 3: Test the comment section feature (1 day)
* Task 4: Test the general forum feature (2 days)
* Task 5: Test the quiz and practice questions feature (3 days)
* Task 6: Test the material management feature (3 days)

**Phase 3: Deployment and Maintenance**

* Task 1: Deploy the system (1 day)
* Task 2: Maintain the system ( ongoing)

**Development Milestones**

Here are the revised development milestones:

* Week 1: Complete the user management system and course search by code feature
* Week 2: Complete the comment section feature and general forum feature
* Week 3: Complete the quiz and practice questions feature
* Week 4: Complete the material management feature
* Week 5: Integrate all features and conduct testing
* Week 6: Deploy the system and conduct final testing